## Sprint Planning
Project Name | Agile Manifesto
StakeHolders/Customers/Users | Students
Created By | Instructor
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
Create a web-based platform to educate and engage users about the Agile Manifesto and methodologies. | US001 | Homepage for Agile Manifesto | As a user, I want a visually appealing homepage that introduces Agile, explains its history, and provides easy navigation to explore other sections, so I can quickly understand what the platform offers. | 8 | 1
| US002 | Agile Values and Principles | As a user, I want an interactive page that explains the four Agile values and 12 principles with examples, so I can understand how they work and apply them to my projects. | 3 | 2
| US003 | Resource Library | As a user, I want a resource library where I can learn about Agile practices like Scrum and Kanban, download templates and guides, and easily search and filter resources, so I can find the tools I need to implement Agile effectively. | 5 | 3
| US004 | Collaboration Features | As a user, I want to engage with others through discussion forums and comments on resources, with secure authentication, so I can share ideas, provide feedback, and learn collaboratively. | 8 | 4
Project Link | https://kenguvakowshik.atlassian.net/jira/software/projects/SCRUM/boards/1/backlog